ADOPTED – SEPTEMBER 28, 2021

AGENDA ITEM NO. 36

Introduced by the Human Services and Finance Committees of the:

INGHAM COUNTY BOARD OF COMMISSIONERS

RESOLUTION TO AMEND RESOLUTION #20-319 WITH THE INSTITUTE FOR INTERGOVERNMENTAL RESEARCH (IIR) AND COMMUNITY MENTAL HEALTH AUTHORITY OF CLINTON, EATON AND INGHAM

RESOLUTION #21 – 466

WHEREAS, Ingham County Health Department wishes to amend Resolution #20-319 by extending the effective date through December 31, 2022 and by increasing funding by $17,045, for a total amount not to exceed $110,795; and

WHEREAS, Resolution #20-168 authorized an agreement with the Institute for Intergovernmental Research (IIR) and Community Mental Health Authority of Clinton, Eaton, and Ingham (CEI-CMH), to accept funding for the Building Bridges Between Jails and Community-Based Treatment for Opioid Use Disorder Demonstration Project; and

WHEREAS, Resolution #20-168 also authorized an agreement with CEI-CMH in the amount of $70,000, to offer assistance with navigating the local Substance Use Disorder (SUD) provider network, support systems and resources; and

WHEREAS, Resolution #20-319 amended the terms of Resolution #20-168 by extending the effective date through August 31, 2021; and

WHEREAS, due to the COVID-19 pandemic, the implementation of this project was delayed and IIR has proposed an extension of the agreement through December 31, 2022 and offered an additional $17,045 in funding; and

WHEREAS, ICHD and CEI-CMH have agreed that an extension is necessary in order to fully implement the project; and

WHEREAS, the Health Officer recommends amending Resolution #20-319 by extending the effective date through December 31, 2022 and by increasing funding by $17,045, for a total amount not to exceed $110,795.

THEREFORE BE IT RESOLVED, that the Ingham County Board of Commissioners authorizes amending Resolution #20-319 by extending the effective date through December 31, 2022 and by increasing funding by $17,045, for a total amount not to exceed $110,795.

BE IT FURTHER RESOLVED, that all other terms and conditions of Resolution #20-319 shall remain in effect.

BE IT FURTHER RESOLVED, that the Controller/Administrator is authorized to make any budget adjustments consistent with this resolution.

BE IT FURTHER RESOLVED, that the Chairperson of the Board of Commissioners is hereby authorized to sign any necessary contract documents on behalf of the County after approval as to form by the County Attorney.

HUMAN SERVICES:  Yeas:  Tennis, Sebolt, Slaughter, Trubac, Maiville

Nays:  None     Absent:  Graham, Naeyaert     Approved  09/20/2021

FINANCE:  Yeas:  Grebner, Tennis, Crenshaw, Polsdofer, Stivers, Schafer, Maiville

Nays:  None     Absent:  None     Approved  09/22/2021